FORM 3

Project Proposal Form

All partner organizations wishing to apply to the IHH Humanitarian Relief Foundation must complete the Project Proposal Form, sign it, and attach if there is any documents in English, Arabic or Turkish other than the requested documents. Make sure to fill in all sections of the form and send the filled forms to IHH as soon as they are approved. Organizations applying for funding for the first time should prepare and return a carefully prepared and signed Fund Agreement (Form 1, 2) prior to this form. Signatures on all forms must belong to the Chairman of the Board of Directors or the General Manager / Secretary.

Section 1: Information of the Partner Organization Preparing the Project

  - Give the official and working names of your foundation. (Example: Official Name: Foundation for Human Rights and Freedom - Humanitarian Relief Foundation / Work Name: IHH Humanitarian Relief Foundation)

| Official Name: | Small Kindness Bangladesh |  |
| --- | --- | --- |
| Work Name (if there is any): | Small Kindness Bangladesh (SKB) |  |
| Official Address: | House # 04, Road # 33, Sector # 07 Uttara Model town # Dhaka # 1220, Bangladesh |  |
| Phone Number: | +880258956123 | Fax: +880258956124 |
| E-Mail | kindnessforbeauty@gmail.com | Website: |

Section 2: General Content of the Project

2.1 General Information about Project

| Project name: Adak Aqiqa (Sacrificing Cows) for the Rohingya Refugees, October 2026 |  |
| --- | --- |
| Total Cost of Project: €12,280 | Amount Requested From IHH: €12,280 |
| Project Duration: One month/30 days |  |
| Project manager: Md Abu Huraira | Phone Number: +8801716350626 |
| E-Mail: kindnessforbeauty@gmail.com | Mobile Number: +8801716350626 |

2.2 Project Address Information

| Country: Bangladesh | Region: Chittagong |
| --- | --- |
| City: Chittagong | County/District: Cox’s Bazar |
| Town: Ukhiya | Neighborhood/Village: Hakim-para, Jamtoli |
| Coordinates: Local organizers and volunteers | Distance from the Capital:440 kilometers |
| Population: More than a Million | Muslim Population: 98% |

2.3 If the project will be implemented in more than one place, fill in the table below.

|  | Region | City | Neighborhood / Village: | Cow Quantity | Number of beneficiaries |
| --- | --- | --- | --- | --- | --- |
| 1 | Chattogram | Cox’s Bazar | Jamtoli | 10 | 400 |
| 2 | Chattogram | Cox’s Bazar | Hakim-para | 10 | 400 |
| Total Items |  |  |  |  | 800 |

2.4 Please provide information about the population and socio-economic status of the project area (city, village and town).

Total Population: More than a million

| Type of people; Age limit (Year); Percentage (%). Child; 0 to 15; 40%. Adult; 16-45; 20%. Old; 46-70; 20%. Over aged; 70 – 70+; 20%. Demographic Structure: Types of Gender; Percentage (%). Male; 45%. Female; 55%. |
| --- |
| (If there is any) Refugee and Migrant Population: 200% |  |
| National Revenue: Dependable on donors | Ratio of Population Living Below the Poverty Line: 200% |

| (If there is any) Refugee and Migrant Population: 200% |  |
| --- | --- |
| National Revenue: Dependable on donors | Ratio of Population Living Below the Poverty Line: |
| Literacy Rate: | Less than 20 percent |
| Provide general information about the socio-economic situation of the project area. Since October2017, more than one million Rohingya refugees have sought refuge in Cox’s Bazar, Bangladesh, after fleeing violence and persecution in Myanmar. Today, approximately one million refugees reside in 33 congested camps located mainly in Ukhiya and Teknaf Upazilas. The Rohingya remain one of the world's largest and most protracted refugee populations, relying almost entirely on humanitarian assistance to meet their basic needs. Prolonged displacement, declining humanitarian funding, and limited livelihood opportunities have further increased their socio-economic vulnerability. 1. Livelihoods and Economic Dependence Due to their refugee status, Rohingya refugees are not legally permitted to participate in the formal labor market in Bangladesh. Consequently, households depend largely on food assistance, cash support, and essential services provided by the Government of Bangladesh and humanitarian organizations. Limited income-generating opportunities, mainly through humanitarian cash-for-work activities and small-scale livelihood initiatives, are insufficient to meet household needs. The reduction in humanitarian funding has further weakened household resilience, increasing poverty, food insecurity, and negative coping mechanisms such as child labor and early marriage. 2. Shelter and Living Conditions Most refugees live in temporary shelters constructed from bamboo, tarpaulin, and other lightweight materials on steep, erosion-prone hillsides. The camps remain among the most densely populated refugee settlements in the world, with limited living space, inadequate ventilation, and insufficient privacy. Shelters are highly vulnerable to cyclones, heavy rainfall, landslides, flooding, and fires, requiring continuous maintenance and emergency preparedness. 3. Health and Nutrition Despite the presence of primary healthcare facilities operated by humanitarian agencies, access to quality healthcare remains constrained due to the large refugee population and limited resources. Malnutrition continues to affect children under five, pregnant and lactating women, and other vulnerable groups. Although vaccination campaigns and disease surveillance have improved public health outcomes, the camps remain susceptible to outbreaks of communicable diseases, including acute watery diarrhea, cholera, dengue, measles, and respiratory infections. Mental health needs have also increased significantly due to prolonged displacement and trauma. 4. Education and Child Welfare Educational opportunities remain limited. Children primarily attend Learning Centres following the Myanmar Curriculum, but these facilities often face shortages of classrooms, trained teachers, and learning materials. Many adolescents, especially girls, discontinue education because of household responsibilities, safety concerns, cultural barriers, or early marriage. The lack of accredited education and limited opportunities for youth contribute to frustration and reduced future prospects. 5. Protection and Gender-Based Violence Women, girls, children, older persons, and persons with disabilities face heightened protection risks within the camps. Gender-based violence (GBV), domestic violence, child marriage, trafficking, and exploitation remain persistent concerns. Although humanitarian organizations provide protection services, psychosocial support, and safe spaces, many survivors still face barriers to reporting incidents because of stigma, fear of retaliation, and limited awareness of available services. 6. Water, Sanitation, Hygiene (WASH), and Environmental Challenges The high population density places significant pressure on water supply, sanitation facilities, and waste management systems. While humanitarian partners have established extensive WASH infrastructure, maintaining service quality and promoting good hygiene practices remain ongoing challenges. Environmental degradation resulting from deforestation, fuelwood collection, and land modification has reduced vegetation cover, increased soil erosion, and heightened the risks of landslides and flash flooding during the monsoon season. 7. Social Cohesion and Mental Well-being Nearly nine years of displacement, uncertainty regarding durable solutions, movement restrictions, and declining humanitarian assistance have contributed to growing psychosocial distress among refugees. Anxiety, depression, and trauma-related conditions are increasingly common. Socio-economic hardship has also contributed to rising protection concerns, including insecurity, criminal activities, drug trafficking, and community tensions, highlighting the continued need for livelihood support, psychosocial services, and community-based protection interventions. Overall, the socio-economic situation in the Rohingya camps remains highly fragile. Continued humanitarian assistance and sustainable resilience-building interventions are essential to improve living conditions, strengthen community protection, and enhance the well-being of refugee households while supporting peaceful coexistence with host communities. |  |

2.5 Project Details:

| Brief Description of the Project: | The “Adak Aqiqa (Sacrificing Cows) for the Rohingya Refugees 2026” initiative is a proposed humanitarian food assistance intervention to be implemented by Small Kindness Bangladesh (SKB) in partnership with IHH Humanitarian Relief Foundation. Rooted in the Islamic tradition of Aqiqa, the initiative aims to transform charitable giving into meaningful nutritional support for vulnerable Rohingya refugee families living in the camps of Cox’s Bazar, Bangladesh. Under the proposed October 2026 intervention, SKB will arrange the procurement and halal slaughtering of 20 healthy cattle, in accordance with Islamic principles and appropriate hygiene and food safety standards. The meat will be properly processed, packaged, and distributed among 800 vulnerable Rohingya refugee families. Priority will be given to households with children, pregnant and lactating women, older persons, persons with disabilities, and female-headed households. Due to prolonged displacement, limited livelihood opportunities, and declining access to humanitarian assistance, many Rohingya refugee families continue to face challenges in maintaining a nutritious and diverse diet. The provision of fresh beef will provide an important source of animal protein, contribute to improved dietary intake, and enable vulnerable families to access nutritious food in a dignified manner. With a total proposed budget of €12,280 the project will cover cattle procurement, transportation, slaughtering, meat processing, packaging, quality control, logistics, and distribution costs. The intervention is expected to be completed within approximately one month. Through this initiative, 800 vulnerable families will each receive approximately 2 kg of fresh beef, helping address immediate nutritional needs while promoting the values of compassion, generosity, and solidarity with vulnerable refugee communities. |
| --- | --- |
| Project Rationale: | The Rohingya refugee population in Cox's Bazar continues to face serious food insecurity and nutritional challenges after years of prolonged displacement. Limited livelihood opportunities, continued dependence on humanitarian assistance, and declining donor funding have made it increasingly difficult for vulnerable families to access sufficient and nutritious food. As humanitarian resources remain limited, many refugee households struggle to maintain a diverse and balanced diet, particularly when it comes to accessing animal protein. The proposed project, "Adak Aqiqa (Sacrificing Cows) for the Rohingya Refugees – October 2026," seeks to respond to these nutritional challenges through the Islamic tradition of Aqiqa. Recent humanitarian assessments continue to highlight significant food security concerns in the camps: - Due to ongoing funding constraints, food assistance for Rohingya refugees has been reduced, making it more difficult for families to meet their regular nutritional needs. - Many refugee households continue to experience inadequate or borderline food consumption and have limited opportunities to obtain protein-rich foods such as meat. - Children remain particularly vulnerable to malnutrition, while pregnant and lactating women, older persons, and persons with disabilities face additional nutritional challenges. - In response to limited food availability, many families have adopted coping strategies such as reducing meal sizes, skipping meals, or giving priority to children when distributing available food within the household. In this situation, fresh beef remains an uncommon food item for most refugee families. Although meat is an important source of high-quality protein and essential nutrients, its cost and limited availability make it difficult for vulnerable households to include it in their regular diets. Limited consumption of animal protein can further affect the nutritional well-being, immunity, and physical development of children and other vulnerable household members. The proposed intervention will procure and sacrifice 20 healthy cows in accordance with Islamic halal principles and appropriate hygiene and food safety standards. Fresh beef will then be processed and distributed among 800 vulnerable Rohingya refugee families. Priority will be given to households with children, pregnant and lactating women, older persons, persons with disabilities, and female-headed families. The project will: - Improve access to nutritious animal protein for vulnerable refugee families facing food insecurity. - Support greater dietary diversity and improved nutritional intake, particularly among children and other at-risk groups. - Provide timely and culturally appropriate food assistance to families with limited access to nutritious foods. - Complement existing humanitarian food assistance by providing a valued source of fresh meat to vulnerable households. The project will utilize the Islamic practice of Aqiqa to transform donors' religious contributions into meaningful humanitarian assistance that strengthens dignity, compassion, and solidarity with vulnerable Rohingya families while contributing to addressing their immediate nutritional needs. |
| Project Objectives: | To improve the nutritional well-being, food security, and dignity of vulnerable Rohingya refugee families in Cox's Bazar by providing fresh beef through the halal sacrifice of cows in accordance with the Islamic tradition of Aqiqa. The project will procure and sacrifice 20 healthy cows and distribute fresh beef among 800 vulnerable Rohingya refugee families, helping increase access to high-quality animal protein and supporting improved dietary diversity. Specific Objectives: - Support the Most Vulnerable Households: Prioritize households with children, pregnant and lactating women, older persons, persons with disabilities, and female-headed families to address the nutritional needs of those facing the greatest vulnerabilities. - Complement Existing Food Assistance: Provide nutritious fresh beef to families affected by reduced humanitarian food assistance and limited access to protein-rich foods, thereby complementing existing food security interventions. - Promote Dignity and Cultural Appropriateness: Distribute beef, a culturally familiar and highly valued food within the Rohingya community, in a manner that respects religious beliefs, cultural practices, and the dignity of beneficiaries. - Strengthen Faith-Based Humanitarian Solidarity: Utilize the Islamic practice of Aqiqa to channel the generosity of Muslim donors toward the urgent nutritional needs of Rohingya refugees, promoting compassion, social responsibility, and solidarity. - Ensure Quality, Accountability, and Transparency: Conduct all project activities—including cattle procurement, halal slaughtering, hygienic meat processing, packaging, transportation, and distribution—in accordance with humanitarian principles, food safety requirements, and appropriate accountability mechanisms, while maintaining close coordination with relevant camp authorities and stakeholders. |
| Target group: | Needy Rohingya Refugees of All Ages |
| Total number of Beneficiaries: | 800 Beef Packages for 800 Needy Rohingya Refugee Families |
| Groups that may be negatively affected by the project: (if there is any): N/A |  |
| Problems that may arise as a result of the project and measures that can be taken: (if there is any) | The proposed project involves the procurement, halal sacrifice, processing, and distribution of fresh beef to vulnerable Rohingya refugee families. While the intervention is expected to generate significant nutritional and humanitarian benefits, certain operational and external risks may affect implementation. SKB has identified these potential challenges and will implement appropriate mitigation measures to ensure the project is carried out efficiently, safely, and transparently. 1. Delays in Cattle Procurement or Price Fluctuations Potential Challenge: Seasonal demand or fluctuations in local livestock markets may affect the timely procurement of healthy cattle or increase procurement costs. - Conduct advance market assessments and procurement planning. - Purchase cattle from reliable local suppliers through a transparent procurement process. - Maintain flexibility in procurement scheduling while ensuring quality |
|  | 2. Food Safety and Meat Quality Potential Challenge: Delays in slaughtering, processing, transportation, or distribution may affect the freshness and safety of the beef. Mitigation Measures: - Complete slaughtering and distribution within the shortest possible timeframe. - Apply strict food hygiene and halal handling procedures. - Use clean food-grade packaging and conduct quality checks throughout the distribution process. 3. Distribution and Crowd Management Potential Challenge: High beneficiary turnout may result in congestion, delays, or disorder during distribution. - Coordinate with the Camp-in-Charge, site management authorities, and community volunteers. - Distribute beef according to verified beneficiary lists and scheduled time slots. - Implement effective crowd management measures to ensure safe and orderly distribution. 4. Inclusion of the Most Vulnerable Potential Challenge: Older persons, persons with disabilities, or seriously ill beneficiaries may face difficulties accessing distribution points. - Prioritize vulnerable households during beneficiary selection. - Provide assistance or doorstep delivery where necessary. - Work closely with community leaders and volunteers to identify and support those with limited mobility. 5. Environmental and Public Health Concerns Potential Challenge: Improper disposal of slaughter waste may create environmental pollution, unpleasant odors, or public health risks. Mitigation Measures: - Dispose of animal waste in accordance with camp regulations and WASH guidelines. - Coordinate with camp authorities to ensure environmentally safe and hygienic waste management practices. 6. Weather and Operational Disruptions Potential Challenge: Heavy rainfall, flooding, or adverse weather conditions may disrupt transportation and distribution activities. Mitigation Measures: - Monitor weather forecasts and prepare contingency plans. - Adjust implementation schedules when necessary and coordinate closely with camp authorities to minimize disruptions. By applying these mitigation measures and maintaining close coordination with relevant authorities and humanitarian partners, SKB will ensure that the project is implemented in a timely, transparent, accountable, and culturally appropriate manner, maximizing benefits for vulnerable Rohingya refugee families. |

Project Supplementary Forms:

Note: Additional forms sent regarding the details of the project must be filled.

For different project proposals such as permanent projects, water wells, and orphanages, the documents specified in the relevant annex must be completed. All documents, including attachments, will be signed.

SECTION 3: Project Implementation and Internal Audit

3.1 Explain step by step how your foundation will implement the project, mentioning all the details.

The project will be implemented by Small Kindness Bangladesh (SKB) in the Rohingya refugee camps of Cox's Bazar in close coordination with the Camp-in-Charge, relevant camp authorities, and humanitarian partners. SKB will follow a transparent, accountable, and well-coordinated implementation process to ensure that all activities comply with Islamic principles, humanitarian standards, and donor requirements.

Step 1: Planning and Coordination

- Obtain the necessary approvals from the Camp-in-Charge and relevant camp authorities.

- Conduct implementation planning meetings with project staff and volunteers.

- Coordinate with humanitarian stakeholders to ensure smooth implementation and avoid duplication.

- Prepare and verify beneficiary lists in consultation with camp representatives, giving priority to vulnerable households.

Step 2: Procurement of Cattle - Procure 20 healthy cows from reliable local suppliers through a transparent procurement process. - Conduct veterinary health checks where applicable to ensure the cattle are healthy and suitable for sacrifice. - Transport the cattle safely to designated slaughter locations. Step 3: Halal Sacrifice and Meat Processing - Carry out the sacrifice in accordance with the Islamic principles of Aqiqa and halal requirements. - Engage experienced Muslim slaughterers under the supervision of SKB staff. - Process, weigh, package, and store the beef using hygienic food handling practices and food safety standards. - Ensure proper disposal of slaughter waste in accordance with environmental and WASH guidelines. Step 4: Distribution of Beef - Distribute fresh beef to 800 vulnerable Rohingya refugee families using pre-approved beneficiary lists. - Give priority to households with children, pregnant and lactating women, older persons, persons with disabilities, and female-headed households. - Ensure the distribution is conducted safely, fairly, transparently, and with respect for beneficiaries' dignity. - Record beneficiary signatures or other appropriate verification to confirm receipt. Step 5: Monitoring, Documentation, and Reporting - Monitor implementation throughout all stages to ensure quality and compliance. - Document activities through photographs, attendance records, beneficiary feedback, and monitoring reports. - Submit a comprehensive narrative and financial report to IHH Humanitarian Relief Foundation, including project achievements, beneficiary statistics, financial expenditures, and supporting documentation. Internal Audit and Accountability SKB has established strong financial management and internal control systems to ensure donor funds are utilized efficiently, transparently, and for their intended purpose. Financial Management - A dedicated finance team will manage the €12,280 project budget in accordance with SKB's financial policies and donor requirements. - All expenditures will be supported by purchase orders, invoices, receipts, payment vouchers, and other relevant financial documents. Internal Audit and Compliance - SKB's internal audit team will review procurement procedures, financial transactions, supporting documents, and beneficiary records to verify compliance with organizational policies and donor regulations. - Random verification visits and post-distribution monitoring will be conducted to confirm that assistance has reached the intended beneficiaries. Transparency and Accountability - Regular implementation updates will be shared with the donor throughout the project period. - A final narrative and audited financial report will be submitted upon project completion, highlighting achievements, lessons learned, challenges encountered, and recommendations. Community Feedback and Complaint Mechanism - Beneficiaries will have access to multiple feedback channels, including community focal persons, complaint boxes, and designated contact numbers. - All complaints and feedback will be documented, investigated, and resolved promptly in accordance with SKB's safeguarding, accountability, and protection policies. - Through effective coordination, transparent implementation, and rigorous internal oversight, SKB will ensure that the project is delivered efficiently, donor resources are managed responsibly, and vulnerable Rohingya refugee families receive timely and dignified humanitarian assistance.

3.2 Please state the experience and ability of your foundation to successfully carry out this project. If you have carried out a project similar to this project before, please provide information.

Since its establishment, Small Kindness Bangladesh (SKB) has been actively engaged in humanitarian and development initiatives across Bangladesh, with a strong presence in the Rohingya refugee camps in Cox's Bazar. The organization has a proven track record of implementing food distribution, nutrition support, WASH, seasonal programs, and emergency relief interventions for vulnerable communities, including displaced populations.

Organizational Capacity - Skilled Team: SKB employs experienced project staff, logisticians, finance officers, and trained volunteers who are familiar with the operational dynamics of the Rohingya refugee camps. Staff members have received training in safeguarding, humanitarian accountability, and the Prevention of Sexual Exploitation and Abuse (PSEA), ensuring compliance with international humanitarian standards. - Local Presence: With an operational presence in Cox's Bazar and established coordination with Camp-in-Charge, site management authorities, and humanitarian partners, SKB is well-positioned to effectively plan and implement humanitarian assistance programs. - Strong Accountability Mechanisms: The organization maintains robust financial management systems, internal control procedures, regular internal audits, and community feedback mechanisms, including complaint boxes, hotline services, and email communication, ensuring transparency, accountability, and donor confidence. Relevant Past Experience SKB has successfully implemented several projects of a similar nature, demonstrating its capacity to implement the proposed Adak Aqiqa project. - Qurbani Meat Distribution Projects (Eid-ul-Adha): Each year, SKB has partnered with national and international donors to procure, sacrifice, and distribute cattle and goats among thousands of Rohingya refugees and vulnerable host community families in Cox's Bazar. These projects included halal slaughtering, hygienic meat processing, packaging, and equitable distribution. - Seasonal Feeding and Ramadan Iftar Projects: SKB has organized large-scale cooked meal and Iftar distribution programmers during Ramadan and other seasonal humanitarian responses, benefiting thousands of vulnerable Rohingya households with nutritious and culturally appropriate meals. - General Food Distribution Support: In partnership with humanitarian organizations, SKB has implemented emergency food assistance and relief distribution programmers in Cox's Bazar, particularly during periods of increased food insecurity and humanitarian need. Proven Ability to Deliver Through these experiences, SKB has developed: - Strong logistical expertise in large-scale livestock procurement, halal slaughtering, meat processing, packaging, and distribution while maintaining high standards of hygiene and food safety. - Effective coordination mechanisms with the Camp-in-Charge, site management authorities, and humanitarian partners to ensure compliance with camp regulations. - The capacity to rapidly mobilize qualified staff and trained volunteers to deliver humanitarian assistance safely, efficiently, transparently, and with dignity, even in challenging camp environments. Given this strong institutional experience and operational capacity, SKB is fully capable of implementing the "Adak Aqiqa (Sacrificing Cows) for the Rohingya Refugees – October2026" project efficiently, transparently, and in full compliance with Islamic principles, humanitarian standards, and donor requirements.

3.3 Provide detailed information about your foundation's internal control mechanism for the implementation of this project.

SKB has established comprehensive internal control and accountability mechanisms to ensure that donor resources are utilized efficiently, transparently, and in accordance with organizational policies, donor requirements, and humanitarian standards. The following internal control systems will guide the implementation of the "Adak Aqiqa (Sacrificing Cows) for the Rohingya Refugees – October 2026" project. 1. Financial Control and Transparency - Dedicated Financial Oversight: All project funds will be managed by SKB's Finance Department under the supervision of the Finance Manager, ensuring compliance with approved financial procedures and donor requirements. - Dual Authorization System: All payments, procurements, and fund disbursements will require joint authorization from the Project Manager and the Finance Manager to strengthen financial accountability and minimize the risk of misuse. - Standard Accounting Practices: SKB follows internationally accepted accounting procedures, maintaining complete financial records supported by vouchers, invoices, receipts, and bank documents to ensure a clear audit trail. 2. Procurement and Asset Control - Procurement Committee: A procurement committee will oversee the purchase of cattle and other required materials through a transparent and competitive procurement process, ensuring value for money and compliance with quality standards. - Supplier Verification: Suppliers will be selected based on their credibility, market reputation, and compliance with halal, health, and quality requirements. - Inventory and Asset Management: Project materials and equipment will be properly recorded, monitored, and managed throughout the implementation period. 3. Operational Monitoring and Supervision - Field Supervision: Designated project staff will supervise cattle procurement, halal slaughtering, meat processing, packaging, and distribution to ensure compliance with project plans, hygiene standards, and humanitarian principles. - Implementation Documentation: Standard monitoring checklists, beneficiary records, and distribution documentation will be maintained to verify project activities and outputs. 4. Internal Audit and Compliance - Internal Audit: SKB's internal audit team will conduct periodic reviews and random spot checks of financial records, procurement documents, and project activities to verify compliance with organizational policies and donor requirements. - Post-Distribution Monitoring (PDM): Random beneficiary verification and field monitoring will be conducted to confirm that assistance reached the intended households and that the distribution process was fair, transparent, and dignified. - Compliance with Standards: The project will be implemented in accordance with SKB's internal policies, humanitarian principles, food safety requirements, and applicable donor guidelines. 5. Safeguarding and Community Feedback - Feedback and Complaint Mechanism: Beneficiaries will have access to complaint boxes, community focal persons, and designated contact numbers to report concerns, complaints, or suggestions. - Safeguarding Measures: All project personnel and volunteers will comply with SKB's safeguarding policies and the Prevention of Sexual Exploitation and Abuse (PSEA) framework to ensure the protection of all beneficiaries, particularly women, children, older persons, and persons with disabilities. 6. Reporting and Donor Accountability - Financial Reporting: SKB will prepare comprehensive financial reports supported by all relevant financial documents and internal verification records. - Narrative Reporting: A detailed narrative report will be submitted upon project completion, summarizing project implementation, beneficiary reach, achievements, challenges, lessons learned, beneficiary feedback, and recommendations. These internal control mechanisms will ensure that the project is implemented efficiently, transparently, and accountably, while safeguarding donor resources and ensuring that assistance reaches the intended Rohingya refugee families in a timely and dignified manner.

Section 4: Project Cost and Sustainability

For this proposal, specify all budget details and add supporting documents where appropriate (At least 3 quotes, estimates, architectural plans, site maps, plan permits, detailed case studies /socio-economic evaluations, registration/registration certificates, references, recommendations, etc.) If necessary, you can present information on additional pages:

4.1 Write the cost items of the project. (Depending on the nature of your project, you can change the table to indicate the project costs in all details, or you can send it as an additional if needed)

| Main Cost Table |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| SL: | Definition | Measure | Qty | Unit Cost |  | Total Cost |  |
|  |  |  |  | BDT | EURO | BDT | EURO |
| 1 | Cow Purchase | No | 20 | 81868 | 584,77 | 1,637,360 | 11,695.40 |
| Sub-Total |  |  |  |  |  | 1,637,360 | 11,695.40 |
| Admin Cost |  |  |  |  |  | 81,844 | 584,60 |
| Grand Total |  |  |  |  |  | 1,719,204 | 12,280 |

Conversion rate:1euro = BDT 140

4.2 Is this proposal to fund an existing project?

 Yes                   No

If your answer is Yes, write your evaluations of the current project and state why it is necessary to continue working on the project.

4.3 Provide details on other institutions where you submitted this project and funds obtained.

N/A

4.4 Sustainability of the Project (For Permanent Projects)

When the project is completed, indicate from which source your foundation will obtain the necessary funds to operate the project. (See. Form 1, Subject 8.4) Although the "Adak Aqiqa (Sacrificing Cows) for the Rohingya Refugees – October2026" project is designed as a one-time humanitarian intervention, it has the potential to create lasting benefits through strengthened community engagement, institutional learning, and continued faith-based humanitarian support. 1. Nutritional and Social Impact - The project will provide vulnerable Rohingya families with access to high-quality animal protein, improving dietary diversity and addressing immediate nutritional needs. - Providing beef, a culturally accepted and religiously valued food, will enhance beneficiaries' dignity, well-being, and social inclusion. 2. Community Engagement and Local Capacity - The project will actively engage community volunteers, trained Muslim slaughterers, and camp authorities throughout implementation. - This collaborative approach strengthens local coordination mechanisms and enhances community participation in future humanitarian activities. 3. Replicable Humanitarian Model - The implementation approach—including transparent procurement, halal slaughter, hygienic meat processing, packaging, and fair distribution—will serve as a practical model for future Aqiqa, Qurbani, and other food assistance programs. - Experiences and lessons learned will improve the quality and efficiency of similar interventions implemented by SKB in the future. 4. Continued Donor Engagement - Successful implementation and transparent financial management will strengthen the confidence of existing and prospective donors. - SKB will continue mobilizing support from individual Muslim donors, charitable organizations, and humanitarian partners to implement similar faith-based humanitarian initiatives in the future. 5. Institutional Sustainability - All project documentation, financial records, monitoring reports, and lessons learned will be maintained within SKB's organizational knowledge management system. - These resources will strengthen institutional capacity and support the planning and implementation of future humanitarian projects. 6. Coordination with Humanitarian Stakeholders - The project will be implemented in close coordination with the Camp-in-Charge, camp authorities, and relevant humanitarian partners, ensuring alignment with existing humanitarian coordination mechanisms and avoiding duplication of assistance. - Strong coordination will contribute to more effective and sustainable humanitarian programming in the refugee camps. - Future Funding As this is a time-bound humanitarian intervention, no recurrent operational funding will be required after the project is completed. However, SKB will continue to mobilize financial support from IHH Humanitarian Relief Foundation, other international humanitarian partners, Islamic charitable organizations, corporate donors, and individual philanthropists to implement similar Aqiqa, Qurbani, and emergency food assistance programmers for vulnerable Rohingya refugees in the future. In summary, while the project is not a permanent programmed, its humanitarian, nutritional, institutional, and operational benefits will contribute to future faith-based humanitarian initiatives and strengthen SKB's capacity to respond effectively to the ongoing needs of Rohingya refugees

Section 5: Control List

Present the documents you added about the project. (Special requirements regarding the type of project are attached.)

- At least 3 offers that indicate market prices

- Region Map

- Detailed Case Studies / Social-Economic Evaluations,

- Others.

Section 6: Pledge

We who have the signatures below (please write the name of your institution) Chairman of the Board of Directors and Chief Executive Officer / General Manager / G. Secretary, confirm that we have previously read all aspects of the Fund Agreement of the IHH Humanitarian Relief Foundation and accepted in writing. In addition, we confirm that we have given correct answers to all the questions above, to the best of our knowledge.

All requests are included in the annex and we undertake that the funds will be used in line with the purpose if the IHH Humanitarian Relief Foundation agrees to provide funds.

Note: Can only be signed by people who are authorized to sign (signatory). All pages must be signed. All documents must be signed and sent after scanning. (PDF, JPG)

| Chairman of the Board of Directors Full Name: Dr. Orakatul Jannat Sign: Date | General Manager / G. Secretary Full Name: Md. Abu Huraira Sign: Date: |
| --- | --- |