FORM 3

Project Proposal Form

All partner organizations wishing to apply to the IHH Humanitarian Relief Foundation must complete the Project Proposal Form, sign it; and attach if there are any documents in English, Arabic or Turkish other than the requested documents. Make sure to fill in all sections of the form and send the filled forms to IHH as soon as they are approved. Organizations applying for funding for the first time should prepare and return a carefully prepared and signed Fund Agreement (Form 1, 2) prior to this form. Signatures on all forms must belong to the Chairman of the Board of Directors or the General Manager / Secretary.

Section 1: Information of the Partner Organization Preparing the Project

  - Give the official and working names of your foundation. (Example: Official Name: Foundation for Human Rights and Freedom - Humanitarian Relief Foundation / Work Name: IHH Humanitarian Relief Foundation)

| Official Name: | Small Kindness Bangladesh |  |
| --- | --- | --- |
| Work Name (if there is any): | Small Kindness Bangladesh (SKB) |  |
| Official Address: | House # 04, Road # 33, Sector # 07, Uttara, Dhaka # 1230, Bangladesh |  |
| Phone Number: | +880258956123 | Fax: +880258956124 |
| E-Mail | info@smallkindnessbd.org | Website: www.smallkindnessbd.org |

Section 2: General Content of the Project

2.1 General Information about Project

| Project name: Distribution of Goats Clothing Food Packets for Rohingya Refugees |  |
| --- | --- |
| Total Cost of Project: € 14280 | Amount Requested From IHH: € 14280 |
| Project Duration: One month/ 30 days |  |
| Project manager: Safwanur Rahman | Phone Number: +8801716350626 |
| E-Mail: info@smallkindnessbd.org | Mobile Number: +8801716350626 |

2.2 Project Address Information

| Country: Bangladesh | Region: Chittagong |
| --- | --- |
| City: Cox’s Bazar | County: Ukhiya, Teknaf |

| Town: Ukhiya, Teknaf | Neighborhood/Village: Kutupalong, Balukhali, Jamtoli |
| --- | --- |
| Coordinates: Local organizers and volunteers | Distance from Capital: 440 km |
| Population: Approximately 1,100,000 | Muslim Population: 100% |

2.3 If the project will be implemented in more than one place, fill in the table below.

| Sl | Region | City | Neighborhood / Village: | Item & Pack Quantity | Number of beneficiaries |
| --- | --- | --- | --- | --- | --- |
| 1 | Chittagong | Cox’s Bazar | Ukhiya, Teknaf | 50 Goats & 150 Orphan Clothing Packages, 250 Food packet | 25 Rohingya Families (50 Goats) & 150 Orphans, 250 family (Food packet) |

2.4 Please provide information about the population and socio-economic status of the project area (city, village and town).

| Total Population: 1,100,000 |  |
| --- | --- |
| Demographic Structure: Gender: Male 45%, Female 55% Age Structure: Child (0-15): 40%, Adult (16-45): 30%, Elderly (46-70): 20%, Over 70: 10% |  |
| Refugee and Migrant Population: 100% |  |
| National Revenue: Completely dependent on humanitarian aid | Ratio of Population Below Poverty Line: 100% |
| Literacy Rate: Less than 10% |  |
| Socio-Economic Situation Over 960,000 Rohingya refugees reside in 33 overcrowded camps in Cox’s Bazar, fleeing persecution in Myanmar. Refugees are restricted from formal employment, making them entirely dependent on humanitarian aid. High levels of poverty, food insecurity, lack of income generating sources and clothing shortages persist, particularly among orphaned children and female-headed households. Livelihood support through livestock rearing (goats) and protection support through clothing distribution address core needs. Since August 2017, over 960,000 Rohingya refugees have taken shelter in Cox’s Bazar, Bangladesh, fleeing violence and persecution in Myanmar. They now reside in 33 densely populated camps, primarily located in Ukhiya and Teknaf Upazilas. The socio-economic condition of this population remains extremely vulnerable and dependent on humanitarian assistance. 1. Livelihoods and Economic Dependence Due to their refugee status, Rohingya are not permitted to engage in formal employment in Bangladesh. As a result, the majority are dependent on aid provided by the government and humanitarian agencies for food, shelter, and basic needs. Limited livelihood opportunities—mainly through NGO-facilitated cash-for-work programs-create high levels of poverty, food insecurity, and frustration, particularly among youth and able-bodied men. 2. Shelter and Living Conditions Rohingya refugees live in temporary shelters made of bamboo and tarpaulin on hilly, erosion-prone land. These makeshift settlements are overcrowded, with inadequate space, ventilation, and privacy. The camps are highly vulnerable to landslides, cyclones, and monsoon-related flooding, making shelter a persistent concern. 3. Health and Nutrition Although humanitarian organizations have set up health clinics and emergency medical services, the camps face serious health challenges. Malnutrition—especially among children under five, pregnant and lactating women—is widespread. Access to maternal care, clean water, and essential medicines is improving but remains insufficient given the scale of need. Outbreaks of communicable diseases such as cholera, diphtheria, and acute watery diarrhea pose ongoing risks. 4. Education and Child Welfare Formal education is restricted for Rohingya children. Learning opportunities are provided through temporary Learning Centers using the Myanmar curriculum, but these are often under-resourced and overcrowded. Many adolescents, particularly girls, are excluded from education due to cultural norms, safety concerns, or early marriage, exposing them to protection risks. 5. Protection and Gender-Based Violence Rohingya refugees—especially women, girls, and unaccompanied minors—are at high risk of gender-based violence (GBV), human trafficking, exploitation, and abuse. Access to justice is limited, and reporting mechanisms are often underutilized due to fear, stigma, or lack of trust. Child marriage and domestic violence are common within the camps. 6. WASH and Environmental Stress The dense population in the camps puts pressure on water, sanitation, and hygiene (WASH) services. While basic WASH infrastructure has been established, maintenance and behavior change remain ongoing challenges. Deforestation caused by initial settlement and fuelwood collection has led to severe environmental degradation, increasing the risk of landslides and reducing ecosystem resilience. 7. Social Dynamics and Mental Health The prolonged displacement, combined with restrictions on movement and future uncertainty, has led to increased frustration, mental distress, and a sense of hopelessness among the Rohingya population. Social cohesion is fragile, and rising security incidents, drug abuse, and criminal activities reflect deepening socio-economic stress. |  |

2.5 Project Details:

| Brief Description of the Project: | Since the outbreak of violence in August 2017, over 960,000 Rohingya refugees have sought shelter in Bangladesh, fleeing persecution and atrocities in Myanmar’s Rakhine State. Currently residing in overcrowded and disaster-prone camps in Cox’s Bazar, these displaced populations continue to endure severe hardships, including limited access to food, livelihoods, clothing, and survival necessities. The situation remains critical, particularly for orphans, women-headed households, and families without a regular source of income. In response to these pressing needs, Small Kindness Bangladesh (SKB), with generous funding from IHH, is launching a targeted humanitarian initiative aimed at improving both immediate welfare and long-term resilience for vulnerable Rohingya families. This project will provide 50 goats to 25 families (2 goats per family with 1-year feed support: 6 packets grain husk), improving nutrition and creating sustainable livelihood opportunities through milk production and animal rearing. Clothing packages for 150 orphans, ensuring dignity, protection, and comfort. 250 food packets for improving nutrient quantity. The project, with a total budget of € 14280 (BDT 1944023), will directly benefit 275 Rohingya families and 150 orphaned children (total 1525 targeted people) through essential distribution and livelihood support. SKB will ensure fair, needs-based beneficiary selection prioritizing widows, female-headed households, persons with disabilities, and large families. In addition to distributions, SKB will provide basic orientation on livestock care and follow-up support to promote asset sustainability. Through this vital project, IHH and SKB reaffirm their commitment to standing beside the Rohingya community in their struggle for safety, dignity, and hope. |
| --- | --- |
| Project Rationale: | Since August 2017, Bangladesh has hosted one of the largest refugee populations in the world in Cox’s Bazar. The lack of sustainable livelihood opportunities and access to basic necessities has significantly increased aid dependency among Rohingya refugees. Orphans often lack appropriate seasonal clothing, while vulnerable families struggle daily to secure nutritious food. In this context, this project funded by IHH directly addresses two critical needs: nutrition/livelihoods through goat rearing and child protection/dignity through clothing distribution. Goats provide food security and reproductive livestock assets, while clothing packages uphold child dignity. This initiative provides an impactful, sustainable, and dignified response to the ongoing humanitarian crisis. |
| Project Objectives: | Overall Objective: To enhance the well-being, dignity, and self-reliance of vulnerable Rohingya refugee families and orphans in Cox’s Bazar through targeted humanitarian assistance and livestock livelihood support. Specific Objectives: • To improve household nutrition and income generation by providing 275 vulnerable families with pairs of goats (50 goats total) along with food packets to 250 families. • To uphold the basic needs, comfort, and dignity of orphaned children by distributing comprehensive clothing packages to 150 orphans. • To prioritize and assist the most marginalized groups, including widows, female-headed households, and orphan-headed families, through transparent selection. • To strengthen long-term resilience through orientation and veterinary follow-up on animal health and feed management. |
| Target Group: | Vulnerable Rohingya Refugee Families & Orphans residing in Cox’s Bazar Camps (Ukhiya and Teknaf) |
| Total Beneficiaries: | 275 Rohingya Families (50 Goats), 150 Orphan’s cloth and 250 family food packet (Total 1525target beneficiary) |
| Groups Negatively Affected: | N/A |
| Potential Problems & Mitigation: | N/A |

Project Supplementary Forms:

Note: Additional forms sent regarding the details of the project must be filled.

For different project proposals such as permanent projects, water wells, orphanages, the documents specified in the relevant annex must be completed. All documents, including attachments, will be signed.

SECTION 3: Project Implementation and Internal Audit

3.1 Explain step by step how your foundation will implement the project, mentioning all the details.

Project Implementation Methodology: Step 1: Initial Planning and Coordination Conduct coordination meetings with Camp-in-Charge (CiC) offices, RRRC, and site management authorities. Prepare detailed implementation plans, procurement timelines, and obtain necessary security clearances. Step 2: Beneficiary Selection & Verification In collaboration with CiC offices and Majhis, SKB will identify vulnerable households prioritizing widows, female-headed families, persons with disabilities, and verified orphans. Final beneficiary lists will be verified with consent and signatures. Step 3: Procurement of Goats & Clothing Form a Purchase Committee as per SKB procurement policy. Collect quotations from verified vendors. Select healthy, vaccinated breeding-age goats (female with kid) and inspect clothing sets before delivery. Step 4: Livelihood Orientation on Animal Care Organize orientation sessions for goat beneficiaries on livestock care, feeding schedule (Glume grain husk), shelter, and disease prevention. Step 5: Ceremonial Distribution Coordinate distribution schedule with camp authorities. Distribute 50 goats to 25 families (2 goats + 6 packets of feed per family) and 150 clothing packages and 250 food packets with photo documentation and signed distribution cards. Step 6: Post-Distribution Follow-up Field officers and livestock specialists will visit households regularly to monitor goat health, feeding, and clothing usability. Step 7: Monitoring, Evaluation & Reporting Track output indicators, gather beneficiary feedback, and submit comprehensive narrative, financial, and photographic reports to IHH. Step 8: Project Closure & Handover Share outcomes with camp authorities and document lessons learned.

3.2 Please state the experience and ability of your foundation to successfully carry out this project. If you have carried out a project similar to this project before, please provide information.

Organizational Capacity and Past Experience SKB is a nationally registered non-profit organization established in 2000, with over two decades of experience in implementing humanitarian and development programs across Bangladesh, including within Rohingya refugee camps and host communities in Cox’s Bazar. SKB’s mission is to empower disadvantaged communities—particularly women, children, orphans, and vulnerable populations—through rights-based, participatory, and sustainable development approaches. SKB has been working continuously and relentlessly for the benefit of neglected and uncared Rohingya orphan children, aiming to bring them into the mainstream of care, education, and dignity. This work has been carried out in collaboration with various national, multinational, and international organizations, including IHH, WAMY, Yetim Vakfi, ICNA, Al Ihsan, HAUK, HHRD-USA, Crescent Aid International, Muslim Aid, Iqra Foundation, WEFA, and others. Through these partnerships, SKB has established itself as a reliable and compassionate actor in the Rohingya humanitarian response. In addition to its livelihood and protection work, SKB delivers a wide range of essential medical services to Rohingya refugees. This includes primary health care, maternal and child health services, medical camps, emergency referrals, and distribution of medicines and hygiene kits. SKB’s medical team works in close coordination with the Camp-in-Charge (CiC), health sector partners, and the local health authorities to ensure timely and accessible care for the refugee population. Operational Capacity: Field Presence: SKB maintains an active field team based in Cox’s Bazar, including experienced project officers, livestock specialists, trainers, and female community mobilizers. Safeguarding and PSEA: All staff are trained in safeguarding and protection from sexual exploitation and abuse (PSEA), and a focal person is designated for all protection issues. Monitoring & Accountability: The organization has robust M&E systems, including regular reporting, beneficiary feedback mechanisms, post-distribution monitoring, and financial tracking. Community Trust: SKB has long-standing working relationships with Majhis, Camp-in-Charge offices, and local coordination mechanisms, ensuring smooth implementation and community engagement. With a solid track record in logistics, coordination, orphan care, and transparent service delivery, SKB is fully prepared and capable of carrying out the proposed project in collaboration with the donor partner IHH, ensuring quality, accountability, and lasting impact for Rohingya families.

3.3 Provide detailed information about your foundation's internal control mechanism for the implementation of this project.

To ensure the successful and accountable implementation of the project titled “Distribution of Cow, Goat, Sewing Machine, and Umbrella for Rohingya Refugees in Bangladesh 2025”, SKB has established a robust internal control framework guided by organizational policies, donor compliance standards, and humanitarian best practices. These mechanisms are designed to minimize risks, prevent misuse of resources, ensure timely delivery, and guarantee beneficiary satisfaction. 1. Governance and Oversight - The project will be overseen by SKB’s Executive Director and Senior Management Team (SMT), who provide strategic direction, decision-making, and accountability. - A Project Steering Committee will be formed to review progress, monitor risks, and ensure alignment with donor expectations and sectoral guidelines. 2. Procurement and Financial Control - All procurements will follow SKB’s Procurement Policy, which emphasizes transparency, value for money, and competitive bidding. - A Purchase Committee will handle quotation collection, vendor evaluation, and selection. Vendor performance and product quality will be verified before approval. - Financial transactions will be monitored by SKB’s Finance Department using double-entry accounting and internal financial software. - All payments will be made via bank transfers or mobile financial services (MFS) to ensure traceability and avoid cash handling. - Periodic financial audits will be conducted internally and externally to ensure financial integrity and compliance with donor (IHH) requirements. 3. Logistics and Asset Management - Distribution items will be physically inspected and tagged by the logistics team before delivery. - A warehouse register and asset tracking system will be maintained to monitor stock movement and ensure secure handling. - Detailed distribution plans and delivery schedules will be prepared, coordinated with the Camp-in-Charge (CiC), and shared with stakeholders to avoid duplication or conflict. 4. Staff Roles and Accountability - The project will be managed by a dedicated Project Manager with support from field coordinators, community mobilizers, livestock specialists, and M&E officers. - Each staff member’s role, responsibility, and deliverables are clearly defined through Terms of Reference (ToR) and monitored through performance tracking. - Code of Conduct and Safeguarding Guidelines are strictly enforced, and all staff are trained on anti-fraud, anti-corruption, and PSEA (Protection from Sexual Exploitation and Abuse). 5. Monitoring, Evaluation, and Feedback a. A Monitoring and Evaluation (M&E) framework will be used to track progress, outcomes, and impact using predefined indicators. b. Regular field visits, spot checks, and post-distribution monitoring will be conducted to verify proper use of distributed items. c. Beneficiary feedback will be collected through: - Complaints and Response Mechanism (CRM): Hotline, feedback boxes, and face-to-face reporting. - Focus Group Discussions (FGDs) and individual interviews. d. All complaints will be logged, investigated, and resolved by the Accountability and Safeguarding Focal Person. 6. Documentation and Reporting - All beneficiary records, distribution forms, receipts, and photo documentation will be securely stored and backed up digitally. - Monthly progress reports, along with financial utilization updates, will be shared with stakeholders. A final project report, including success stories, challenges, and recommendations, will be submitted upon project completion.

Section 4: Project Cost and Sustainability

For this proposal, specify all budget details and add supporting documents where appropriate (At least 3 quotes, estimates, architectural plans, site maps, plan permits, detailed case studies / socio-economic evaluations, registration / registration certificates, references, recommendations, etc.) If necessary, you can present information on additional pages:

4.1 Write the cost items of the project. (Depending on the nature of your project, you can change the table to indicate the project costs in all details or you can send it as an additional if needed)

| Sl | Main Cost Table |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Definition | Mea sure | Qua ntity | Unit Price |  | Total Price |  |
|  |  |  |  | BDT | EURO | BDT | EURO |
| 1 | Goat purchasing cost with 1-year feed (2 goats per family) | No. | 25 | 30553 | 223 | 763825 | 5575 |
| 2 | Orphan clothes purchasing cost | No. | 150 | 2310 | 16.9 | 346500 | 2535 |
| 3 | Food packet distribution | No. | 250 | 3009 | 21.96 | 752250 | 5490 |
|  | Subtotal Direct Implementation Cost |  |  |  |  | 1862575 | 13600 |
|  | Admin Cost (5%) |  |  |  |  | 93129 | 680 |
|  | Grand Total Requested Budget |  |  |  |  | 1955704 | 14280 |
|  | Conversion rate: 1 EURO= BDT137 |  |  |  |  |  |  |

Budget details: Goat purchasing

| Income Generating Project |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Goat Rearing Project |  |  |  |  |  |  |
| Goat Rearing Unit Cost |  |  |  |  |  |  |
| SL | Items of Expenditure |  | Quantity | Unit cost | Total Cost |  |
|  |  |  |  |  | BD | EURO |
| 1 | Goat per family (Goat with kid) |  | 2 | 11264 | 22528 | 164.44 |
| 2 | Animal Feeding for one year | Glume (grain husk) Packets | 6 | 1337.5 | 8025 | 58.58 |
| Subtotal withiout administrative cost |  |  |  |  | 30553 | 223 |

Budget details: Dress Distribution

| Orphan Cloth Unit Cost |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Per Male Orphan’s Cost |  |  |  |  |  |
| Project Cost |  |  |  |  |  |
| Items to Buy | Unit: Cost |  | Amount | Total Cost |  |
|  | Euro | BDT |  | Euro | BDT |
| Pajama/Pant | 4.05 | 550 | 1 | 4.05 | 550 |
| Panjabi /shirt | 6.72 | 920 | 1 | 6.72 | 920 |
| Shoes (Sandal) | 6.13 | 840 | 1 | 6.13 | 840 |
| Total: (without administrative cost) |  |  |  | 16.9 | 2310 |

| Per Female Orphan’s Cost |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Project Cost |  |  |  |  |  |
| Items to Buy | Unit: Cost |  | Amo unt | Total Cost |  |
|  | Euro | BDT |  | Euro | BDT |
| Salwar | 3.29 | 450.00 | 1 | 3.29 | 450 |
| Kameez | 6.87 | 940.00 | 1 | 6.87 | 940 |
| Urna | 1.98 | 270.00 | 1 | 1.98 | 270 |
| Shoes (Sandal) | 4.76 | 650.00 | 1 | 4.76 | 650 |
| Total: (without administrative cost) |  |  |  | 16.9 | 2310 |

Budget details: Food Packet Distribution

| Rohingya Refugee Relief-2026 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Food Packet Distribution |  |  |  |  |  |  |  |
| Food Packet Budget Costing (Fifteen days Package for one family consisting of four/five members) |  |  |  |  |  |  |  |
| Sl | Particulars | Measure | Qua ntity | Unit Price |  | Total Cost |  |
|  |  |  |  | BDT | EURO | BDT | EURO |
| 1 | Date (Khorma) | Kg | 2 | 555 | 4.05 | 1110 | 8.10 |
| 2 | Sugar | Kg | 2 | 137 | 1.00 | 274 | 2.00 |
| 3 | Noodles (Family pack) | Packet | 2 | 195 | 1.42 | 390 | 2.84 |
| 4 | Chick peas/Raw vetch | Kg | 4 | 112 | 0.82 | 448 | 3.28 |
| 5 | Onion | Kg | 2 | 84 | 0.61 | 168 | 1.22 |
| 6 | Mustard oil | liter | 0.5 | 310 | 2.26 | 155 | 1.13 |
| 7 | Garlic | Kg | 1 | 225 | 1.64 | 225 | 1.64 |
| 8 | Chilli Powder | Kg | 0.2 | 645 | 4.71 | 129 | 0.94 |
| 9 | Packaging | Number | 1 | 20 | 0.15 | 20 | 0.15 |
| 10 | Carton | Number | 1 | 70 | 0.51 | 70 | 0.51 |
| 11 | Labor (Load/unload) | Number | 1 | 20 | 0.15 | 20 | 0.15 |
|  | Total Amount before overhead Cost |  |  |  |  | 3009 | 21.96 |
| Note -01: Price may fluctuate during implementation period. |  |  |  |  |  |  |  |
| Note -02: Rice, oil, Pulse and Salt: These four food items are being provided by WFP (World Food Program). Government is not allowing any NGO to distribute those foods. |  |  |  |  |  |  |  |
| Note -03: Packet size and unit cost may vary according to availability of product and distribution rules of camp authority, but total cost would be the same. |  |  |  |  |  |  |  |
| Conversion rate: 1 EURO= BDT137 |  |  |  |  |  |  |  |

4.2 Is this proposal to fund an existing project?

 Yes                       No

If your answer is Yes, write your evaluations of the current project and state why it is necessary to continue working on the project.

4.3 Provide details on other institutions where you submitted this project and funds obtained.

N/A

4.4 Sustainability of the Project (For Permanent Projects)

Please specify the source from which your organization will obtain the funding required to operate the project once it is complete. (See: Form 1 Item 8.4) Future Funding and Sustainability Strategy To ensure that the project’s impact is sustained beyond the immediate distribution phase, SKB has developed a forward-looking strategy to secure additional resources and support for ongoing operation, follow-up, and beneficiary empowerment. 1. Donor Engagement and New Partnerships - SKB will actively pursue follow-up funding opportunities from existing and new donors, including international NGOs, foundations, and faith-based humanitarian organizations with a history of supporting Rohingya-related work. - The organization will prepare project impact reports, success stories, and beneficiary case studies to present to potential donors for scaling or extending support. - SKB has established long-term partnerships with donors such as IHH, WAMY, ICNA, Al Ihsan, HHRD, Muslim Aid Sverige, HAUK, and others, and will engage them for supplementary or continuation funding. 2. Integration with Ongoing Projects - Beneficiaries of this project (e.g., livestock and dress recipients) will be linked with existing SKB programs in livelihoods, healthcare, and skills development. - This ensures continued follow-up, training, and advisory support without requiring separate project-specific funding. 3. Local Resource Mobilization - Where feasible, SKB will seek community contributions and in-kind support (e.g., veterinary services, training space, tailoring inputs) from host community leaders, local businesses, and well-wishers. - SKB has previously mobilized Zakat, Sadaqah, and Qurbani funds from philanthropic partners for related interventions and plans to continue using these sources to support project participants. 4. Income from Livelihood Outputs - The project promotes self-reliance by enabling beneficiaries to generate income through animal rearing and tailoring. Profits earned can be reinvested by families into sustaining or expanding their small enterprises. - SKB will offer guidance and referral support to help beneficiaries access local markets or value chains for milk, livestock, and tailored products. 5. Volunteer and Community Support Network - SKB’s trained community volunteers and mobilizers will continue to monitor and support beneficiaries as part of their routine activities under broader community outreach programs. - Through this multi-pronged approach—combining donor engagement, program integration, income generation, and local support—SKB aims to sustain the project’s benefits and ensure that the impact continues to grow even after the initial implementation period.

Section 5: Control List

Present the documents you added about the project. (Special requirements regarding the type of project are attached.)

- At least 3 offers that indicate market prices

- Region Map

- Detailed Case Studies / Social-Economic Evaluations,

- Others.

Section 6: Pledge

We who have the signatures below Small Kindness Bangladesh (SKB) Chairman of the Board of Directors and Chief Executive Officer / General Manager / G. Secretary, confirm that we have previously read all aspects of the Fund Agreement of the IHH Humanitarian Relief Foundation and accepted in writing. In addition, we confirm that we have given correct answers to all the questions above, to the best of our knowledge.

All requests are included in the annex and we undertake that the funds will be used in line with the purpose if the IHH Humanitarian Relief Foundation agrees to provide funds.

Note: Can only be signed by people who are authorized to sign (signatory). All pages must be signed. All documents must be signed and sent after scanning. (PDF, JPG)

| Chairman of the Board Full Name: Dr. Orakatul Jannat Signature: Date: 08/10/2026 | General Manager / Secretary/ED Full Name: Md. Abu Huraira Signature: Date: 08/10/2026 |
| --- | --- |