SMALL KINDNESS BANGLADESH (SKB) WORKS PORTAL

Program Officer & Executive Operational Guide (7-Step Project Lifecycle)

Document Reference: SKB-SOP-2026-V3 | System URL: https://skbportal.online/projects

# 1. Executive Summary & Purpose

The SKB Works Portal is Small Kindness Bangladesh's centralized, multi-tenant digital management system designed for humanitarian and development projects. It enforces standardized compliance across donor contracts (such as IHH Turkey, Turkish Diyanet, Qatar Charity), government approvals (NGO Affairs Bureau & RRRC), financial audits, and field execution.

# 2. The 7-Step Interconnected Project Lifecycle

| Step # | Tab Name | Route | Operational Purpose |
| --- | --- | --- | --- |
| 1 | 1. Project Charter | /projects/[id]/charter | Master 12-Section Charter, 6-Line Budget, GPS Coordinates, RACI Governance, and 4-Executive Sign-Offs. |
| 2 | 2. Stage Gates | /projects/[id]/kanban | Automated control engine guarding 6 project stages from Inception to Form-7 Closure. |
| 3 | 3. Logframe Tree | /projects/[id]/logframe | M&E Logical Framework Hierarchy (Goal -> Outcome -> Output -> Activity -> Indicators). |
| 4 | 4. Tasks & Workplan | /projects/[id]/tasks | Detailed task execution workplan assigned to RACI officers with target due dates. |
| 5 | 5. Beneficiaries | /projects/[id]/beneficiaries | Encrypted beneficiary register, NID duplicate checking, and consent management. |
| 6 | 6. Compliance Docs | /projects/[id]/documents | Document repository (MOUs, SWIFT receipts, asset handovers) synced with Donor Portal. |
| 7 | 7. Closing & Audit | /projects/[id]/closing-report | 4-Domain Pre-Submission Audit Working Paper, 5-Executive Sign-Offs, and Form-7 ZIP unlock. |

# 3. Data Interconnection Pipeline

Information flows automatically from Step 1 (Project Charter) through to Step 7 (Closing & Form-7 Audit). The Stage Gate engine dynamically checks data integrity across all 7 steps before authorizing stage transitions.